Getting Started

Planning an Event

Whether the event is a diocesan centennial Eucharist in a large arena, or a parish bazaar or fundraising dinner, an event should be carefully planned, especially if it’s new. Many events that are traditional in a parish or diocese end up with a binder that its leaders follow, or now, a memory stick with the detailed plans discovered after years of practice. But the first and second time through, you often are starting from scratch.

Step One:  Find a Good Leader

Finding the right leader/planner/team is essential as a first step. This will be the group or person who really makes something important happen, who puts in the hard work. Look for someone with experience in event planning or two people who may be less experienced, but willing to work together and support each other in doing something new.  If there is not a good potential leader to be found in the parish or diocese, the first question to ask is whether the event should go forward at all.

Choose leaders who will work with sensitivity to others as well as with determination to get the job done. People are hurt and offended by church volunteers who run roughshod over them. They often leave the church when this happens, never to darken the doors again – not  just of your church but of any church. So find people who can include others, pay attention to them and their ideas, and then thank them appropriately after an event – it’s a faith development imperative.

Step Two:  Develop a Plan

Here’s where the computer is your helper. A simple table is useful and can be updated as the planning process goes on.  A well-used process might look like this:

Plan for Parish Event

| Task | Who | Details | Deadline | Status |
| --- | --- | --- | --- | --- |

And here’s how the first draft of the plan might look:

Plan for Parish Celebration Dinner				Last Updated:  January 30, 2015

| Task | Who | Details | Deadline | Status |
| --- | --- | --- | --- | --- |
| Select a Chair for the event | Wardens/ Rector |  | Sept. 30, 2014 | Done. Sally and Jim Smith have agreed. |
| Choose a date for the dinner | “ | Avoid times when snowbirds are away and cottagers leave. Check when March break is. Not in Lent either. | Sept. 30, 2014 | Done: April 5, 2015 is it. |
| Gather a small working group | S&J | Keep it small. | Oct. 5, 2014 | Done. |
| First meeting of working group | S&J | Get to know each other. Brainstorm ideas. Explore options. Choose someone to keep careful notes and update planning model after each meeting. | Mid-Oct. | Done |
| Choose theme |  |  |  |  |
| Choose caterer |  |  |  |  |
| Develop plan to publicize |  |  |  |  |
| …and so on |  |  |  |  |

And here’s an actual plan that St. Peter’s, Cobourg, Ont., uses each year to develop their annual Advent Conference. This is the final plan that has been adjusted at least monthly during the planning time of six months. But it now works so well that there is only one planning meeting and the rest of the follow-through is done by trusted members of the planning committee and reported in by email or phone. (Better than a binder by far!!) This plan takes us to the start of the event. There’s another plan for the event itself to be sure all details of the process of the two-day conference are covered. Most names have been exchanged for initials.

Plan for Annual Advent Conference    November 28, 29		Updated:  November 1

Theme:  “God as One of Us”

Hosted by St. Peter’s Church, Cobourg		Speaker:  The Rt. Rev. Ann Tottenham

Go-To Person:  KM			Facilitator:  SPL

| Time | Topic | Lead | Where | Details |
| --- | --- | --- | --- | --- |
| Pre-Conference | Decide budget Invite speaker Recruit planning committee Design format of conference Design worship Recruit music lead Recruit catering help for lunch Recruit registrar Publicize (poster, registration, email blasts etc.) Recruit welcomers, people to do snack breaks and welcome coffee Get audio person to oversee set-up and use Offer child care and recruit person to provide if needed Recruit “runner” for speaker Reserve room at Woodlawn if needed Recruit someone to lead meditation |  |  | Done Done Done. Included deanery people for first time Done Under way (RM) AS said yes. KP and the M&M group will do break. SPL confirmed JK to do lunch. JK will link with KP re muffins for the morning break. DONE NM in place; SF is back-up and on site person for the weekend if NM cannot come. EG will do poster. DONE EG did distribution of notices and posters to deanery and education groups. SPL to provide registration form to go with poster. SPL to draft public announcement for local papers and radio and distribute to members to send out; Church announcements by EG (Brighton), SM and SPL (St. Peter’s), SF (St. John’s), LB (Perrytown), ND for Gore’s Landing, SS (eastern part of deanery), SO (Grafton); SPL to put ad in free sections of newspaper in Cobourg/Port Hope; EG in Brighton newspaper Committee to be welcomers. Snacks and coffee on Saturday morning by AK SM to ask JP or DD to look after sound system Child care requested by only one family…we’ll provide an honorarium for a babysitter rather than set up a child care program at the church this time. SPL tasked BM. DONE SPL to ask speaker if this is needed/wanted. Asked Oct. 22. Room reserved Oct. 23. SM to ask SD. DONE |
| WEDNESDAY, NOVEMBER 26 | Confirm if children are coming | SPL |  | Call NM to check registration requests |
|  | Confirm tasks being undertaken for the conference | SPL |  |  |
| FRIDAY, NOVEMBER 28 |  |  |  |  |
| 2:00 | Set-up of Sheppard Hall, lectern, tables, chairs, sound system, LCD (if needed), registration table, name tags, extra chairs in chapel if required, flip chart etc.; lunch for Saturday Set up for evening reception Ensure adequate copies of Worship book and handouts Set up sound system Bring talking sticks | Planning committee, PA SM and team SPL SM/JP SPL | Hutton Room | SM to ask PA Set up in circle format if possible with the numbers SF to set up registration, welcoming station SM to be helper Have several talking sticks for Saturday discussion |
| 3- ish | Ann to arrive | SPL |  | Give tour and deal with any issues; intro concept of runner |
| 4-ish | Set up worship space in Sheppard Hall | ? |  |  |
| 5-6:30 | Quiet Dinner (at Woodlawn?) | Ann |  |  |
|  | Runner to greet Ann and be there to help her | BM |  |  |
| 6:00-7 | Registration begins at 6:30 | SF and team AK Ann and FR SPL to find someone Child minder | Hallway, or wherever is best | Hand out Worship booklets and nametags, etc. Have tea and coffee and water available for people as they come and gather. SPL asked Oct. 22 Assign readings and prayers, etc. as people come in; try to get people not from St. Peters as well as the usuals. Bring water jugs up to Sheppard Hall Welcome children and bring them upstairs to their spot (not needed this year) |
| 6:50-7:00 | Herd people to plenary area; intro children to child care | Planning Committee |  |  |